## Sheet1
Priority By Category | Strategy |  | Lead | Alternate | Status/Accomplishments
Completed July 2019 | Walking Audit (WA) |  | Yvonne Murphy - Edgecombe County Cooperative Extension | BOC | The Mayor and BOC of Pinetops seek to improve and promote safe and healthy options for all residents to be physically active within the Town. An initial walking audit will be conducted to aid in this process. June 11, 2019, Town and County officials, residents, and key stakeholders (18 participants) carried out a walk audit to assess walkability in key places downtown Pinetops. Representatives at the audit included: Town Commissioners of Pinetops, Department of Public Health, Upper Coastal Plain Rural Planning Organization, Edgecombe County Health Department, EdgecombeCounty Cooperative Extension, Edgecombe County Public Schools and Edgecombe County Government. The group used the “Walkability Checklist” available from Move More Walk Now NC to assess walkability in the community. After conducting the audit, the team met to debrief and brainstorm on short and long-term goals based on the audit findings. (Supporting documents in 2019 Pinetops Walking Audit Folder)
| In-Town Roadways | Primary streets downtown Pinetops do not have pedestrian crosswalks nor pedestrian crossing signs. Some streets sidewalks are cracked and broken and, in some areas, there are no sidewalks at all to allow connectivity throughout the town.
Completed August 2020 | WA Action 1.1 | Install Wayfinding signage in town and key points along regular walking routes | Yvonne Murphy - Edgecombe County Cooperative Extension | BOC | Edgecombe County Cooperative Extension designed and funded 22 Wayfinding signage for the Town of Pinetops. The primary information/directional sign with a map of the town, streets, and key points of interest was installed on Hamlet Street across from Town Hall. All other signs were placed in highly visible areas along various walking routes.
1 | WA Action 1.2 | Develop and implement a plan for pedestrian street crosswalk lanes. Mark major street crossings, intersections, and other specific locatons with crosswalk lanes and install pedestrian crossing signage. (Date) | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator | May 6, 2022 The Town of Pinetops requested NCDOT support for cross walks in Town on highways NC 43 and 122. Both routes are scheduled for resurfacing in 2025 Highway Maintenance Improvement Program (HMIP). This may be an opportunity to install the cross walks on those routes if they are feasible. May 9, 2022 the Town Administrator sent email to Mr. Paul Marak (NCDOT) the requested documents needed to initiate an assess/evaluate to determine crosswalk requirements. January 2, 2023, Town sent application letter for NCDOT TAP Grant for Highway 42 through Town for sidewalks and crosswalks. Town Administrator Fred Ventresco met with Gray Keeter, NCDOT Halifax Branch, in Pinetops on 3/22/23, and toured him around pertinent areas in need of sidewalks, crosswalks, and related. Gray informed that there was possibly only one more crosswalk they could do, the one on 2nd and Hamlet, and also said that TAP funds will not help with sidewalks, only with crosswalks.
| WA Action 1.3 | Develop and implement a plan to install/replace/improve sidewalks on high traffic streets within the city limits of Pinetops. Some areas do not have sidewalks and many other sectors require major upgrades/repairs. (Date) | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator | North Carolina Upper Coastal Plain Rural Planning Organization (UCPRPO) Strategic Transportation Investments (STI) Project P6 BIKE-PED, Spot ID# B170684 - Construct sidewalk along NC 43 (E Hamlet Street) from S Sally Jenkins Street to 16th Street and to Vidant walking trail. NCDOT cost $105K (April 2022, project dropped from NCDOT 2024-2033 State Transportation Improvement Program (STIP) due to lack of qualification and funding. The Town will resubmit the project in the future to include the installation of a sidewalk along South NC42/43 (E Hamlet Street) from South Van Street (Devonshire Apartments) to South 7th Street.
Completed August 2021 | Pinetops Community Economic Development Assessment Plan (PCEDAP) |  | BOC |  | January 18, 2021, the Pinetops Board of Commissioners (BOC) created Local working group consisting of Pinetops citizens and emplyees, key stakeholders, support from NC State University, Rural Forward NC, and MSRPC. The Team developed PCEDA survey to solicite citizen input/feedback. Survey initiative implemented and completed January 21 - February 21, 2021. The working group presented the assessment and draft PCEDAP to the Town BOC for review, input and approval on June 22, 2021. The BOC adopted the plan August 3, 2021. Next Step: Develop a plan and timeline for implementaion (Supporting documents in 2021 Community Economic Development Assessment Folder)
PCDAB Work Plan | Healthy, Sustainable Small-Town Living (PCEDAP Goal #1) | People and families looking for a place to live and work want to have choices - especially when it comes to matters of health. This includes food, health services, healthy activities and recreational opportunities. | See PCDAB Work Plan for details
PCDAB Work Plan | Active, Inclusive Town (PCEDAP Goal #2) | Does Pinetops offer enough of what new residents are looking for? Fitness centers, restaurants, breweries, shops, festivals, events and places to gather are some of those amenities to attract younger people and their families. | See PCDAB Work Plan for details
Completed August 2, 2022 | PCEDAP Action 2.1 | Organize a Downtown Advisory Committee or Economic Development Group based on the Main Street® model in 1st quarter FY22 (Partner: MSRPC). | Bruce Naegelen - NC Main Street & Rural Planning Center (MSRPC), NC Department of Commerce Oscar Mabry - Commissioner | BOC | December 7, 2021 Pinetops BOC approved moving forward with the development of an organizational structure for a new downtown/community advisory committee. December 14, 2021 Mayor Brenda Harrel signed Memorandum of Understanding (MOU) with Mr. Bruce Naegelen, NC Main Street & Rural Planning Center (MSRPC) to facilitate the process. April 5, 2022 BoC adopted Bylaws, Town Ordinance, and Candidate Application for the Pinetops Community Development Advisory Board (PCDAB). The BoC also appointed Candidate Interview Committee (Mayor, Mayor Pro Tem, Administrator). April 6, 2022 posted advertisement for candidates; will advertise for positions until June 15, 2022. August 2, 2022 the BoC accepted and appointed 5 PCDAB members and 2 alternates. (Supporting documents in PCDAB Folder)
Completed October 13, 2022 | PCEDAP Action 2.2 | Develop and implement training sessions for staff and PCDAB members by Apr 2022. | Bruce Naegelen - NC Main Street & Rural Planning Center (MSRPC), NC Department of Commerce | BOC | Mr. Naegelen has developed an orientation and three training sessions for BOC and PCDAB. The orientation and first training session completed August 30, 2022, second session completed September 8, 2022, and final session completed October 13, 2022.
Completed January 18, 2023 | PCEDAP Action 2.3 | Develop and adopt a two year work plan | PCDAB | BOC | See PCDAB Work Plan for details
PCDAB Work Plan | Destination for Rural Entrepreneurship (PCEDAP Goal #3) | With abundant high-speed internet available in all parts of town will provide an opportunity to develop Pinetops as an entrepreneurial destination and new business start-ups. The process will require planning, creating partnerships, and town investment to create an encouraging environment of entrepreneurship. | PCDAB | BOC | See PCDAB Work Plan for details
| Inclusive, Communicative Government (PCEDAP Goal #4) | A transparent, communicative and inclusive government is mandatory for a community to achieve economic success. During this Assessment process, we learned there are improvements government leaders can make to reach the economic positioning/vision for Pinetops.
Completed February 2022 | PCEDAP Action 4.1 | Hire a new Town Administrator by Dec 31, 2021. | BOC |  | June – August 2021, the Town of Pinetops Board of Commissioners (BOC) reviewed/revised the current Town Administrator job description and established a Candidate Selection Committee (CSC) that included the Mayor and two Commissioners. With the aid of the Upper Coastal Plain Council of Governments (UCPCOC), the CSC established a Town Administrator Search Process. The position was then posted on the Town of Pinetops and UCPCOC websites, with all applications submitted/forawrded to UCPCOC for screening and vetting. The UCPCOC provided the BOC with 5 qualified candidates. Of the 5, the CSC narrowed the applicants down to 3 candidates for interviews. During the interview process, one of the 3 applicants deferred an interview, and the remaining candidates were interviewed yet rejected by the BOC. Next Step: November 2021 - re-list/advertise the Town Administrator position and initiate another screening/vetting process. January 12, 2022 the appointed committee conducted a second round of interviews of listed candidates. A candidate was selected and accepted the position. The BoC voted and approved candidate for the position at the February 1, 2022 BoC meeting.
1 | PCEDAP Action 4.2 | Develop a communication plan and implement by Nov 1, 2021 to inform residents and businesses of all populations about news, activities, events. (Date) | Fred Ventresco - Town Administrator | BOC | 1. Town of Pinetops has developed and implemented a bi-monthly newsletter, 2. Developed and implemented The Pinetops Community Development Advisory Board, 3. Considering implementing a Town newspaper.
2 | PCEDAP Action 4.3 | Develop town policies and procedures to remove barriers for all residents to be heard and involved about town issues. Then incorporate the necessary changes by Dec 31, 2022. | Fred Ventresco - Town Administrator | BOC
Administration
3 | Personnel Action 1 | Review and revise Town Personnel Manual by (Date) | Fred Ventresco - Town Administrator | BOC
2 | Personnel Action 2 | Develop personnel appraisal/evauation form and implement a regular documented reviews of employee's job performance and contribution to his/her department and the Town by (Date). This process would ensure a better workplace environment, improve the business of the Town, and opportunities to reward high-achieving workers. | Fred Ventresco - Town Administrator | Department Supervisors
1 | Personnel Action 3 | Many employee positions of the Town of Pinetops do not have sufficient job descriptions. It is essential for each position to have a detailed written job descriptions with essential information about the job responsibilities, activities, qualifications, and skills for a specific job. Review all Town employees positions and duties and develop adequate job discriptions for employees by (Date) | Fred Ventresco - Town Administrator | Department Supervisors | Completed job descriptions: Town Administrator, Electric Line Technician, General Utility Worker, Director Public Works & Utilities (Job descriptions posted in Administration - Job Descriptions Folder)
Information Technology (IT)
1 | IT Action 1 | The Town of Pinetops IT infrastructure is outdated and needs major upgrades. There are 4 main areas of concern: Town Adminstration Office, Police Department, Utilities Department, and Fire Department. An IT assessment must be conducted to determine methods to be productive in today's enviroment. (Date) | Will Williams - MRL Network Solutions Fred Ventresco - Town Administrator | Odyssey Brown - Town Clerk Oscar Mabry - Commissioner | January 5, 2021, MRL Network Solutions conducted an assessment of the Town system to determine current status. The assessment identified many issues (e.g. incompatible software, outdated licenses, outdated computers, server replacement). MLR provided a project list with associated costs to identify and make recommendations for short and long term goals to upgrade system. May 11, 2021 BOC approved $25K for IT upgrades including funding for Pineview Cemetery software in the FY22 budget to support IT projects. Next Step: Coordinate with MRL to prioritize and start improvements (Supporting documents in Information Technology Folder)
| IT Action 2 | Engage with the Edgecombe County Digital Inclusion Team to develop a Digital Inclusion Program for Pinetops. This program will ensure that all residents, local businesses, and stakeholders will have access to broadband resources. (Supporting documents in Information Technology/Digital Inclusion Folder) | BOC |  | TBD
Public Works/Utilities
4 | Residential Electric KWh Rate | Implement a flat rate kWh charge for residential electricity. The average residential rate/charge, per kWh in Edgecombe County and surrounding municipalities, is 00.11 cent per kWh. The Town of Pinetops charges its residents two levels of electricity rate/charges per kWh (00.1429 cent for 0-750 and 00.1298 cent over 750 kWh). | Fred Ventresco - Town Administrator | BOC | March 29, 2022 BoC voted and approved to establish and implement a residential flat rate for electric KWh charges effective date FY24 (July 2023). Next Step: Conduct a rate study no later than January 2023 to determine actual rate charge.
Terminated March 2022 | Utilities Billing Format | The Town of Pinetops utility billing is not transparent. The monthly bill does not reflects the multiple levels of rate charges for residents to see their usages for electricity, water, and sewage service. The estimated cost to reformat billing software is $14K. | BOC | Oscar Mabry - Commissioner | March 29, 2022 BoC voted and approved to terminate action to revamp residential utilities billing format due to going to a flat rate for residential electric KWh charges. The flat rate will clear up many concerns regarding residents reading and understanding their monthly utility bill.
| Waste Water Ttreatment Plant Rehabilitation (WWTP) | The WWTP is required to meet the total nitrogen and phosphorus limits in accordance with the National Pollutant Discharge Elimination System (NPDES) permit program. This program addresses water pollution by regulating point sources that discharge pollutants to waters of the United States. The Town of Pinetops facility requires major modifications to ensure sustainability and comply with regulatory requirements. The current WWTP system has been online and operational since 1985 (35 years), and many components of facility are nearing the end of service life and needs replacement. The approach is to conduct an Asset Inventory and Assessment (AIA) to determine the condition and scope of work to upgrade facility. AIA must be accomplished by Professional Engineers (PE). | Carlos Williams - Public Works Department, Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator Oscar Mabry - Commissioner | September 23, 2020, Town Mayor, Administrator, and Town Clerk signed the North Carolina Department of Environmental Quality (NCDEQ) AIA grant application and applicable documents (NCDEQ Division of Water Infrastructure Water and Sewer Financial Information Form, Resolution, Certifications). Sep 25, 2020: The Wooten Company picked up application and supporting documents from Pinetops and delivered to NCDEQ Division of Water Infrastructure. As of Apr 14, 2021, the State Water Infrastructure Authority approved the designation of Town of Pinetops as a Distressed Unit Designation (DUD). The Division of Water Infrastructure and NC Department of State Treasurer indicated the town water system potential meets the criteria of a DUD in accordance with Session Law 2020-79, enacted Jul 1, 2020. DUDs are systems identified that may be struggling to provide services or face other financial or fiscal management challenges that could threaten the long-term viability of the system. April 5, 2022 BoC approved resolutions and applied for State ARPA grants via the Wooten Company for a Sanitary Sewer System AIA and WWTP Rehabilitation. July 2022 the State Division of Water Infrastructure approve a grant in the amount of $150K for a Sanitary Sewer System AIA. But, no funding for the WWTP Rehabilitation project. However, with the AIA the Town will be better prepared with additon data and justifications the next time around. (Supporting documents in WWTP/Resolutions/Utilities Grants Folders)
6 | WWTP Action 1 | Conduct an AIA to determine the condition and scope of work to upgrade facility by April 2024. | Carlos Williams - Public Works Department, Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator Oscar Mabry - Commissioner | Waste Water System AIA notice to proceed was October 27, 2022 by the Wooten Company. Estimated completion date no later than April 2024.
| WWTP Action 2 | Develop a viable plan to ensure long-term sustainablility of the system | Carlos Williams - Public Works Department, Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator Oscar Mabry - Commissioner | TBD
WWTP Action 3
| Town Waterline Improvement (TWI) | The Town of Pinetops waterlines are over 40 years old and requires major overhauls and upgrades. The Division of Water Infrastructure and NC Department of State Treasurer indicated the town water system potential meets the criteria of a DUD in accordance with Session Law 2020-79, enacted Jul 1, 2020. DUDs are systems identified that may be struggling to provide services or face other financial or fiscal management challenges that could threaten the long-term viability of the system. | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator | April 5, 2022 BoC approved resolutions and applied for State ARPA grants via the Wooten Company. July 2022 the State Division of Water Infrastructure approve grants in the amount of $150K for a Water System AIA and $7.96M for waterline Improvements to aid in the upgrades/replacements of disignated waterlines throughtout the town. TWI project notice to proceed was October 27, 2022 by the Wooten Company. Line replacement/upgrades will be scheduled and completed via several phases and task orders due to state requirements (surveys, designs, permitting, bidding). The estimated completion date and closeout no later than April 2025.
5 | TWI Action 1 | Conduct an AIA to determine the condition and scope of work to upgrade facility by April 2024. | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator | Water System AIA notice to proceed was October 27, 2022 by the Wooten Company. Estimated completion date no later than April 2024.
7 | TWI Action 2 | Develop and implement a plan to upgrades/replace disignated waterlines throughtout the town by March 2025. | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator
TWI Action 3
| Pinetops Fats, Oil and Grease (FOG) Ordinance | In accordance with North Carolina Division of Environmental Health, a condition of the Town Wastewater Collection System Permit requires the Town to develop and implement a FOG program for non-residential users. The purpose of the program is to reduce sewer blockage at Food Handling Facilities (FHF) that discharge into the Town’s sanitary sewer system. FHFs must install a grease interceptor or grease trap. Automotive Related Facilities that may contribute petroleum-based oil to the Town’s sanitary sewer system are required to install oil-water separators.
2 | FOB Action 1 | Develop a Town FOG program ordinance and with BOC approval by (Date). | Carlos Williams - Public Works Department | Cody Lancaster-Public Works Supervisor
3 | FOB Action 2 | Identify, inform, and educate citizens and local businesses of ordnance and requirements by (Date). | Carlos Williams - Public Works Department | Cody Lancaster-Public Works Supervisor
FOB Action 3
| Develop and Maintain Pinetops Public Water Service Line (WSL) Inventory | The purpose of the inventory is to identify, replace, report, and manage lead and galvanized water pipes throughout the Town of Pinetops. WSL inventories are the foundation from which water systems take action to address a significant source of lead in drinking water - lead service lines (LSLs). Establishing an inventory of service line materials and identifying the location of LSLs is a key step in getting lines replaced and protecting public health. The Environmental Protection Agency (EPA) intends to take final action on the proposal to revise the Lead and Copper Rule Revisions (LCRR) by October 16, 2024.
1 | WSL Action 1 | Designated Pubic Works personnel/BOC members and the Town Administrator will attend the North Carolina League of Municipalities (NCLM) Webinar (1hour): “What Water Systems Need to Know About the EPA Copper & Lead Rule Revision” on November 16, 2022. | Fred Ventresco - Town Administrator | BOC | Administrator Fred Ventresco, Mayor Brenda Harrell, and Commissioner Oscar Mabry attended the Webinar. Mr. Ventresco will down presentation and share it with Public Works personnel no later than (date).
5 | WSL Action 2 | Complete a Town wide WSL inventory by (Date) | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator
8 | WSL Action 3 | Provide initial WSL inventory to EPA no later than October 16, 2024. | Cody Lancaster-Public Works Supervisor | Fred Ventresco - Town Administrator
| Stormwater Runoff (SWR) Management | There are several main ditches outside the town limits of Pinetops that carry rainwater runoff from within the Town to local tributaries of Town Creek. A work effort has just been completed that has cleaned these “external” ditches from the edge of town to the tributaries/creek. A number of “internal” ditches and storm drains within the Town are currently not operating at capacity due to obstructions (soil, yard debris, trash, etc.). This project will require extensive phases to identify, prioritize and begin the work effort on restoring rainwater run-off capacity from within the Town. It is likely that a combination of resources from with the Town’s Utility Department and outside expertise will be needed to complete this project. | (Supporting documents in Stormwater Runoff Management Folder)
Completed May 2020 | SWR Action 1 | Develop a map, identifying the Town zones and sections of stormwater runoff ditches on the edge of town that carries the runoff to local tributaries and creeks. (Date) | Cody Lancaster-Public Works Supervisor | Dennis Sugg - Commissioner Oscar Mabry - Commissioner | The town was divided into 3 zones including 6 sections that correspond to the external ditches that receive stormwater runoff from specific areas of the Town. (Zone 1 - Sections 1,2) (Zone 2 - Section 6) (Zone 3 - Sections 3,4,5)
| SWR Action 2 | Identify and engage Engineering firm to assist Project Team in determining the work effort, costs and duration by each section of the Town. Determine the extent of work effort needed by section in terms of remediation plan, cost and duration. Utilize a combination of internal and external resources to accomplish each phase of the project. (Date) | Cody Lancaster-Public Works Supervisor | Dennis Sugg - Commissioner Oscar Mabry - Commissioner | September 9, 2020 the Wooten Company provided the Town with a proposal for the scope of services to assess section 1 of the Town’s Drainage Basins. The projected timeline to complete the assessment of section 1 is within 3 months of the notice to proceed (Est cost $15.1K). The projected cost to complete assessments of all zones and sections is $90.6K.
| SWR Action 3 | Develop a detail Project Plan for each section to include available funding options. (Date) | Cody Lancaster-Public Works Supervisor | Dennis Sugg - Commissioner Oscar Mabry - Commissioner
| SWR Action 4 | Present proposed Sectional Project Plan to the BOC for approval. (Date) | Cody Lancaster-Public Works Supervisor | Dennis Sugg - Commissioner Oscar Mabry - Commissioner
Planning & Community Development
| Minimum Housing & Abandoned Structures (MHAS) Project | Within the Town of Pinetops there are dwellings that are unfit for human habitation due to dilapidation, defects increasing the hazards of fire, accidents, and other calamites; lack of ventilation, light and sanitary facilities; and other conditions rending such dwellings unsafe or unsanitary, dangerous, and detrimental to the health, safety, and morals and inimical to the welfare of the town. |  |  | Supporting documents in Minimum Housing and Abandoned Structures Folder and see January 4, 2022 Resolution of Minimum Housing and Abandoned Structures Code Enforcement
Completed January 2022 | MHAS Action 1 | Develop a resolution and adopt a policy for minimum housing and abandoned structures code enforcement. | BOC | Fred Ventresco - Town Administrator | Develop a resolution to adopt a policy for minimum housing and abandoned structures code enforcement. Completed January 4, 2022
1 | MHAS Action 2 | Identify, develop, and maintain a listing with the status of the structures (residential or commercial) most in need of repair and/or demolition. Determine if the funding is available for the Town to demolish the structure in the event of noncompliance by the owner. If possible, determine which homes will be targeted for enforcement prior to budget planning so that a determination can be made if sufficient funds will be available. (Date) | BOC | Fred Ventresco - Town Administrator
2 | MHAS Action 3 | Create a Housing Committee (HC) that will be devoted to fulfilling certain obilgations should the Town of Pinetops receive any Community Development Block Grants (CDBG) related to housing.
Comleted December2023 | MHAS Action 3.1 | BOC approve estiblishing Housing Committee | BOC | Fred Ventresco - Town Administrator | December 5, 2023 the BOC voted and approved to establish the Housing Committee
Comleted December2023 | MHAS Action 3.2 | BOC approve by-laws for Housing Committee | BOC | Fred Ventresco - Town Administrator | December 5, 2023 the BOC voted and approved Housing committee by-laws
MHAS Action 3.3
| Town Ordinance Codification | Review and revise Town Ordinance by (Date) | BOC | BOC
| Recreational Opportunities |  | BOC | Fred Ventresco - Town Administrator